## Sheet1
BUG REPORT
VERSION NO: |  |  |  |  | TESTED BY: Ajeshmon AR
VERIFIED BY: RUGMA MA'AM |  |  |  |  | MODULE NAME : new module
ENIVORNMENT DETAILS: WINDOWS 10 64bit |  |  |  |  | DATE :18\07\24
BUG ID | EXPECTED RESULT | BUG SUMMARY | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS | SCREENSHOT
TL_HP_01 | All the elements should be aligned as properly disalyed | Non-proper display of elements | 1.Open the website 2. explore the website | LOW | High | NEW | https://drive.google.com/file/d/1YZ-N8oojuh7CmhA5BLjrY8iFvHqswYGb/view?usp=sharing
TL_HP_02 | All elements should be readable | All elements are non readable | 1.Open the website 2. explore the website | LOW | HIGH | NEW | https://drive.google.com/file/d/1z_snnq7kVc8v8lZ3rP0wVvP-s4ecipb0/view?usp=sharing
TL_HP_03 | All elements show be properly fit on the view port f the device used contents should be fit into the aspect ratio of the device's screen | All elements show be properly fit on the view port f the device used contents should be fit into the aspect ratio of the device's screen | 1.Open the website 2. explore the website | LOW | HIGH | NEW | https://drive.google.com/file/d/1KtlxdKpSumi7oWPtvkP5w8r6BTi2upRl/view?usp=sharing
TL_HP_04 | only should accept less the user name should only contain two to three spaces | Accepts more than 2-3 spaces | 1.open the webpage 2.signup page 3.enter the details | high | HIGH | NEW | https://drive.google.com/file/d/1OUVVUliKHV394-69xaXQuehfrmobWEbL/view?usp=sharing
TL_HP_05 | the website should throws a pop up message whenever enters a wrong character which is against the criteria mentioned | doesn’t throw a pop up message | 1.open the webpage 2.signup page 3.enter the details | Moderate | High | NEW
TL_HP_06 | shouln't be able to copy the charecters on the password field | does allow the charecters to be copied | 1.open the webpage 2.signup page 3.enter the details | HIGH | HIGH | NEW
TL_HP_07 | Should contain a RE-captcha | Doesn't contain a RE-captcha | 1.open the webpage 2.signup page 3.enter the details | low | moderarte | NEW | https://drive.google.com/file/d/1iEDJ2SIxaXaBCMXWDqBbqKJO7ijGh8OE/view?usp=sharing
TL_HP_08 | Should be a button for resending a resetting link for restteing the password | there is no button for resending the link | 1.open the webpage 2.signup page 3.enter the details | moderate | high | NEW | https://drive.google.com/file/d/1yDTSkzzOTa37_l-IN3BGk4S882fPCKYc/view?usp=sharing
TL_HP_09 | Should exist a timer for resendig the link | there is no timer | 1.open the webpage 2.signup page 3.enter the details | moderate | HIGH | NEW | https://drive.google.com/file/d/1MNsad1WnlZV78WkbMPLghltsKeNkHeio/view?usp=sharing
TL_HP_10 | Searches should give suggestions in a drop down manner | the searches doesn’t give sugeestions | 1.open the webpage 2.signup page 3.enter the details | moderate | HIGH | NEW
TL_HP_11 | All the images should be dispalyed correctly | Images are not dispalyed correctly | 1.open the webpage 2.signup page 3.enter the details | HIGH | HIGH | NEW
TL_HP_12 | All the post should be clickable and readable | the post are not clickable and redirecting | 1.open the website 2.explore the website | HIGH | HIGH | NEW
TL_HP_13 | The timezone should change the area/location | the area/location is not changed while changing the timezone | 1.open the webpage 2.signup page 3.enter the details | LOW | LOW | NEW
TL_HP_14 | should contain an astrid sign on the mandatory field | doesn’t contain an astrid sign | 1.open the webpage 2.signup page 3.enter the details | LOW | HIGH | NEW